## Home
MAYURA SUPERMARKET
Version No: |  |  |  | Verified By:
Tested By: SINIVARGHESE L |  |  |  | Date:19/01/2026
Environmental Details: Windows 10, Chrome
HOME
Test ID | Test Description | Test Step | Test Data | Expected Result | Actual Result | Status
MSM_HP_01 | Check whether page loaded successfully | 1. Open website | https://mayuramart.com/ | Should load successfully | Page loaded successfully | Pass
MSM_HP_02 | Check whether the logo is present in the page | 1. Open site 2.Look for the logo | https://mayuramart.com/ | Should present logo | Logo is present | Pass
MSM_HP_03 | Check whether any other image is appear other than logo | 1. Open site 2. Look for the logo | https://mayuramart.com/ | Should present logo | Logo is present | Pass
MSM_HP_04 | Check whether home page is responsive in all devices | 1. Open website 2. Look for the home page responsiveness in other browsers | https://mayuramart.com/ | Should responsive in all browsers | Responsive in all browsers | Pass
MSM_HP_05 | Check whether feedback button is working or not | 1.Open site 2. Click on feedback button | https://mayuramart.com/ | Should be function properly | Feedback button is working properly | Pass
MSM_HP_06 | Check whether feedback button name field accepting any numbers | 1.Open site 2. Click on feedback button 3.Type numbers in name field | https://mayuramart.com/ | Should not accept any numeric values | Accepting numeric values | Fail
MSM_HP_07 | Check whether feedback button phone number field accepting any alphabets or special characters | 1.Open site 2. Click on feedback button 3.Type alphabets in phone field | https://mayuramart.com/ | Should not accept any alphabets values | Accepting alphabets values | Fail
MSM_HP_08 | Check whether whatsapp button is working or not | 1.Open site 2. Click on whatsapp button | https://mayuramart.com/ | Should be function properly | Whatsapp button is working properly | Pass
MSM_HP_09 | Check whether feedback button email field accepting any invalid email | 1.Open site 2. Click on feedback button 3.Type invalid email data | https://mayuramart.com/ | Should not accept any invalid data | Accepts valid email format | Pass
MSM_HP_10 | Check whether get in touch button is working or not | 1.Open site 2. Click on get in touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_HP_11 | Check whether call us button is working or not | 1.Open site 2. Click on call us touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_HP_12 | Check whether address is visible to read or not | 1.Open site 2. Look on address field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_HP_13 | Check whether welcome to mayoora description is visible to read or not | 1.Open site 2. Look on description field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_HP_14 | Check whether certified organic button is working or not | 1.Open site 2. Click on organic button | https://mayuramart.com/ | Should be function properly | Button is not working properly | Fail
MSM_HP_15 | Check whether huge savings button is working or not | 1.Open site 2. Click on savings button | https://mayuramart.com/ | Should be function properly | Button is not working properly | Fail
MSM_HP_16 | Check whether easy returns button is working or not | 1.Open site 2. Click on easy returns button | https://mayuramart.com/ | Should be function properly | Button is not working properly | Fail
MSM_HP_17 | Check whether parking button is working or not | 1.Open site 2. Click on parking button | https://mayuramart.com/ | Should be function properly | Button is not working properly | Fail
MSM_HP_18 | Check whether all product images are visible or not | 1.Open site 2. Look for the all products | https://mayuramart.com/ | Should be visible all products | Visible allproducts | Pass
MSM_HP_19 | Check whether all product details are correct | 1.Open site 2. Look for the all products | https://mayuramart.com/ | Should be visible and clear all products details | Products details are correct | Pass
MSM_HP_20 | Check whether all customer reviews are visible or not | 1.Open site 2. Look for the customer reviews | https://mayuramart.com/ | Should be visible all reviews | Visible all reviews | Pass

## About
MAYURA SUPERMARKET
Version No: |  |  |  | Verified By:
Tested By: SINIVARGHESE L |  |  |  | Date:19/01/2026
Environmental Details: Windows 10, Chrome
ABOUT US
Test ID | Test Description | Test Step | Test Data | Expected Result | Actual Result | Status
MSM_AU_01 | Check whether page loaded successfully | 1. Open website 2.Click on about us button | https://mayuramart.com/ | Should load successfully | Page loaded successfully | Pass
MSM_AU_02 | Check whether the about us page is redirected when we click on button | 1. Open site 2. Click about us button | https://mayuramart.com/ | Should open page | page is open successfully | Pass
MSM_AU_03 | Check whether any other image is appear other than logo | 1. Open site 2.Click on about us button 3. Look for the logo | https://mayuramart.com/ | Should present logo properly | Logo is present | Pass
MSM_AU_04 | Check whether home page is responsive in all devices | 1. Open website 2. Look for the about page responsiveness in other browsers | https://mayuramart.com/ | Should responsive in all browsers | Responsive in all browsers | Pass
MSM_AU_05 | Check whether feedback button is working or not | 1.Open site 2.Click on about us button 3. Click on feedback button | https://mayuramart.com/ | Should be function properly | Feedback button is working properly | Pass
MSM_AU_06 | Check whether whatsapp button is working or not | 1.Open site 2.Click on about us button 3. Click on whatsapp button | https://mayuramart.com/ | Should be function properly | Whatsapp button is working properly | Pass
MSM_AU_07 | Check whether get in touch button is working or not | 1.Open site 2.Click on about us button 3. Click on get in touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_AU_08 | Check whether call us button is working or not | 1.Open site 2.Click on about us button 3. Click on call us touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_AU_09 | Check whether address is visible to read or not | 1.Open site 2.Click on about us button 3 Look on address field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_AU_10 | Check whether welcome to mayoora description is visible to read or not | 1.Open site 2.Click on about us button 3. Look on description field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_AU_11 | Check whether our mission description is visible to read or not | 1.Open site 2.Click on about us button 3. Look on misson field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_AU_12 | Check whether our vision description is visible to read or not | 1.Open site 2.Click on about us button 3. Look on misson field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_AU_13 | Check whether core values description is visible to read or not | 1.Open site 2.Click on about us button 3. Look on misson field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_AU_14 | Check whether the facebook button is redirected when we click | 1. Open site 2.Click on about us button 3. Click facebook button | https://mayuramart.com/ | Should open page | Facebook page is not open | Fail
MSM_AU_15 | Check whether the twitter button is redirected when we click | 1. Open site 2.Click on about us button 3. Click twitter button | https://mayuramart.com/ | Should open page | Twitter page is not open | Fail
MSM_AU_16 | Check whether the instagram button is redirected when we click | 1. Open site 2.Click on about us button 3. Click instagram button | https://mayuramart.com/ | Should open page | Instagram page is not open | Fail
MSM_AU_17 | Check whether the LinkedIn button s redirected when we click | 1. Open site 2.Click on about us button 3. Click LinkedIn button | https://mayuramart.com/ | Should open page | LinkedIn page is not open | Fail
MSM_AU_18 | Check whether the home button in quick links is redirected when we click | 1. Open site 2.Click on about us button 3. Click home button | https://mayuramart.com/ | Should open page | Home page is not open | Fail
MSM_AU_18 | Check whether the about us button in quick links is redirected when we click | 1. Open site 2.Click on about us button 3. Click about button | https://mayuramart.com/ | Should open page | About page isopening successfully | Pass
MSM_AU_19 | Check whether the brand page button in quick links is redirected when we click | 1. Open site 2.Click on about us button 3. Click brand page button | https://mayuramart.com/ | Should open page | Brand page is opening successfully | Pass
MSM_AU_20 | Check whether the contact us button in quick links is redirected when we click | 1. Open site 2.Click on about us button 3. Click contact us button | https://mayuramart.com/ | Should open page | Contact us page is opening successfully | Pass

## Brands
MAYURA SUPERMARKET
Version No: |  |  |  | Verified By:
Tested By: SINIVARGHESE L |  |  |  | Date:19/01/2026
Environmental Details: Windows 10, Chrome
BRANDS
Test ID | Test Description | Test Step | Test Data | Expected Result | Actual Result | Status
MSM_BR_01 | Check whether page loaded successfully | 1. Open website | https://mayuramart.com/ | Should load successfully | Page loaded successfully | Pass
MSM_BR_02 | Check whether the Brand page is redirected when we click on button | 1. Open site 2. Click brand button | https://mayuramart.com/ | Should open page | page is open successfully | Pass
MSM_BR_03 | Check whether any other image is appear other than logo | 1. Open site 2. Click brand button 3. Look for the logo | https://mayuramart.com/ | Should present logo properly | Logo is present | Pass
MSM_BR_04 | Check whether offer page is responsive in all devices | 1. Open website 2. Click brand button 3. Look for the brand page is responsiveness in other browsers | https://mayuramart.com/ | Should responsive in all browsers | Responsive in all browsers | Pass
MSM_BR_05 | Check whether feedback button is working or not | 1.Open site 2. Click brand button 3. Click on feedback button | https://mayuramart.com/ | Should be function properly | Feedback button is working properly | Pass
MSM_BR_06 | Check whether whatsapp button is working or not | 1.Open site 2. Click brand button 3 Click on whatsapp button | https://mayuramart.com/ | Should be function properly | Whatsapp button is working properly | Pass
MSM_BR_07 | Check whether get in touch button is working or not | 1.Open site 2. Click brand button 3. Click on get in touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_BR_08 | Check whether call us button is working or not | 1.Open site 2. Click brand button 3. Click on call us touch button | https://mayuramart.com/ | Should be function properly | Button is working properly | Pass
MSM_BR_09 | Check whether address is visible to read or not | 1.Open site 2. Click brand button 3.Look on address field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_BR_10 | Check whether all brands are visible or not | 1.Open site 2. Click brand button 3. Look on all brands field | https://mayuramart.com/ | Should be visible properly | Visible to read properly | Pass
MSM_BR_11 | Check whether all brands allignment is properly arranged | 1.Open site 2. Click brand button 3. Look on all brands field | https://mayuramart.com/ | Should be properly alligned | Visible toallign properly | Pass

## Offers
MAYURA SUPERMARKET
Version No: |  |  |  | Verified By:
Tested By: SINIVARGHESE L |  |  |  | Date:19/01/2026
Environmental Details: Windows 10, Chrome
OFFERS
Test ID | Test Description | Test Step | Test Data | Expected Result | Actual Result | Status
MSM_OR_01 | Check whether page loaded successfully | 1. Open website | https://mayuramart.com/ | Should load successfully | Page loaded successfully | Pass
MSM_OR_02 | Check whether the offer page is redirected when we click on button | 1. Open site 2. Click offer button | https://mayuramart.com/ | Should open page | page is open successfully | Pass
MSM_OR_03 | Check whether any other image is appear other than logo | 1. Open site 2. Click offer button 3. Look for the logo | https://mayuramart.com/ | Should present all fields and labels | Logo is present | Pass
MSM_OR_04 | Check whether offer page is responsive in all devices | 1. Open website 2. Click offer button 3. Look for the brand page is responsiveness in other browsers | https://mayuramart.com/ | Should responsive in all browsers | Responsive in all browsers | Pass
MSM_OR_05 | Check whether all labels and buttons are worked properly | 1. Open website 2. Click offer button 3. Look for the all labels and buttons | https://mayuramart.com/ | Should be worked properly | Worked properly | Pass
MSM_OR_06 | Check whether all offer products are visible to read | 1. Open website 2. Click offer button 3. Look for the all product details | https://mayuramart.com/ | Should be visible to read | Visible properly | Pass
MSM_OR_07 | Check whether any product details overlapped with other product images | 1. Open website 2. Click offer button 3. Look for the all product details | https://mayuramart.com/ | Should be arranged properly | All products images arranged properly | Pass

## Contact
MAYURA SUPERMARKET
Version No: |  |  |  | Verified By:
Tested By: SINIVARGHESE L |  |  |  | Date:19/01/2026
Environmental Details: Windows 10, Chrome
CONTACT US
Test ID | Test Description | Test Step | Test Data | Expected Result | Actual Result | Status
MSM_CU_01 | Check whether page loaded successfully | 1. Open website | https://mayuramart.com/ | Should load successfully | Page loaded successfully | Pass
MSM_CU_02 | Check whether the contact us is redirected when we click on button | 1. Open site 2. Click contact button | https://mayuramart.com/ | Should open page | page is open successfully | Pass
MSM_CU_03 | Check whether any other image is appear other than logo | 1. Open site 2. Click contact button 3. Look for the logo | https://mayuramart.com/ | Should present all fields and labels | Logo is present | Pass
MSM_CU_04 | Check whether contact us page is responsive in all devices | 1. Open website 2. Click contact button 3. Look for the brand page is responsiveness in other browsers | https://mayuramart.com/ | Should responsive in all browsers | Responsive in all browsers | Pass
MSM_CU_05 | Check whether all labels and buttons are worked properly | 1. Open website 2. Click contact button 3. Look for the all labels and buttons | https://mayuramart.com/ | Should be worked properly | Worked properly | Pass
MSM_CU_06 | Check whether contact us label is visible to read or not | 1. Open website 2. Click contact button 3. Look for the contact us label | https://mayuramart.com/ | Should be visible properly | Visible properly | Pass
MSM_CU_07 | Check whether location label and details are visible to read or not | 1. Open website 2. Click contact button 3. Look for the location label | https://mayuramart.com/ | Should be visible properly | Visible properly | Pass
MSM_CU_08 | Check whether location button is redirecting to google map location | 1. Open website 2. Click contact button 3. Click on the location button | https://mayuramart.com/ | Should be worked properly | Not redirecting to the location | Fail
MSM_CU_09 | Check whether call now label and details are visible to read or not | 1. Open website 2. Click contact button 3. Look for the call label | https://mayuramart.com/ | Should be visible properly | Visible properly | Pass
MSM_CU_10 | Check whether call now button is redirecting to calling option | 1. Open website 2. Click contact button 3. Click on the call button | https://mayuramart.com/ | Should be worked properly | Call button redirecting to the calling option | Pass
MSM_CU_11 | Check whether email us label and details are visible to read or not | 1. Open website 2. Click contact button 3. Look for the email us label | https://mayuramart.com/ | Should be visible properly | Visible properly | Pass
MSM_CU_12 | Check whether email button is redirecting to email account | 1. Open website 2. Click contact button 3. Click on the email button | https://mayuramart.com/ | Should be worked properly | Not redirecting to the email account | Fail
MSM_CU_13 | Check whether keep in touch label and details are visible to read or not | 1. Open website 2. Click contact button 3. Look for the keep in touch label | https://mayuramart.com/ | Should be visible properly | Visible properly | Pass
MSM_CU_14 | Check whether keep in touch name accepting any numbers or special characters | 1. Open website 2. Click contact button 3.Type on numeric and special characters | https://mayuramart.com/ | Should not accept any numbers or special characters | Accepting numbers and special characters | Fail
MSM_CU_15 | Check whether keep in touch phone field accepting alphabets | 1. Open website 2. Click contact button 3.Type alphabets on phone field | https://mayuramart.com/ | Should not accept any alphabets | Accepting alphabets | Fail
MSM_CU_16 | Check whether keep in touch phone field accepting morethan 13 numbers | 1. Open website 2. Click contact button 3.Type13 numbers on phone field | https://mayuramart.com/ | Should not accept morethan 13 nombers | Accepting morethan 13 numbers | Fail
MSM_CU_17 | Check whether facebook button in the follow us field working properly | 1. Open website 2.Click on contact us 3.Click facebook button | https://mayuramart.com/ | Should be redirected to facebook page | Working properly | Pass
MSM_CU_18 | Check whether instagram button in the follow us field working properly | 1. Open website 2.Click on contact us 3.Click finstagram button | https://mayuramart.com/ | Should be redirected to instagram page | Working properly | Pass

## BUG_REPORT
MAYURA SUPERMARKET
IDENTIFIED BY:SINIVARGHESE L REPORTED TO: ENVIRONMENTAL DETAILS:Windows 10, Chrome DATE:21/01/2026
BUGID | TEST ID | Expected Result | Bug Summary | Steps to Reproduce | Severity | Priority | Screenshot | Status
DEF_MSM_HP_01 | MSM_HP_06 | Name field Should not accept any numeric values | Name field is accepts numeric characters | 1. Open site 2. Click the edit box of name in feedback option 3. Type numeric characters 4.Fill all other and submit | Major | Minor | https://drive.google.com/file/d/18sczLbMKYHDoigzsGABbP4oHBMOFk4Og/view?usp=drive_link | New
DEF_MSM_HP_02 | MSM_HP_07 | Phone number field should not accept any alphabets values | Phone field is accepts alphabet characters | 1. Open site 2. Click the edit box of phone in feedback option 3. Type alphabet characters 4.Fill all other and submit | Major | Minor | https://drive.google.com/file/d/18sczLbMKYHDoigzsGABbP4oHBMOFk4Og/view?usp=drive_link | New
DEF_MSM_HP_03 | MSM_HP_13 | Certified organic button should be function properly | Button is not working properly | 1. Open site 2. Click on Certified organic button | Minor | Minor | https://drive.google.com/file/d/1UH4g2SXjhYfdvjSuqAzY5hAFAogjXY7L/view?usp=drive_link | New
DEF_MSM_HP_04 | MSM_HP_14 | Huge savings button should be function properly | Button is not working properly | 1. Open site 2. Click on huge savings button | Minor | Minor | https://drive.google.com/file/d/1UH4g2SXjhYfdvjSuqAzY5hAFAogjXY7L/view?usp=drive_link | New
DEF_MSM_HP_05 | MSM_HP_15 | Easy returns button should be function properly | Button is not working properly | 1. Open site 2. Click on easy returns button | Minor | Minor | https://drive.google.com/file/d/1UH4g2SXjhYfdvjSuqAzY5hAFAogjXY7L/view?usp=drive_link | New
DEF_MSM_HP_06 | MSM_HP_16 | Parking button should be function properly | Button is not working properly | 1. Open site 2. Click on parking button | Minor | Minor | https://drive.google.com/file/d/1UH4g2SXjhYfdvjSuqAzY5hAFAogjXY7L/view?usp=drive_link | New
DEF_MSM_HP_07 | MSM_AU_14 | Facebook button should redirect when we click on button | Facebook page is not opening | 1. Open site 2.Click on about us button 3. Click facebook button | Minor | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_08 | MSM_AU_15 | Twitter button should redirect when we click on button | Twitter page is not opening | 1. Open site 2.Click on about us button 3. Click twitter button | Minor | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_09 | MSM_AU_16 | Instagram button should redirect when we click on button | Instagram page is not opening | 1. Open site 2.Click on about us button 3. Click instagram button | Minor | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_10 | MSM_AU_17 | LinkedIn button should redirect when we click on button | LinkedIn page is not opening | 1. Open site 2.Click on about us button 3. Click LinkedIn button | Minor | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_11 | MSM_AU_18 | Home button in quick links should redirect when we click | Home page is not opening | 1. Open site 2.Click on about us button 3. Click home button | Major | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_12 | MSM_CU_08 | Location button should redirect to google map location | Location not redirecting | 1. Open website 2. Click contact button 3. Click on the location button | Major | Major | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_13 | MSM_CU_12 | Email button should redirect to email account | Not redirecting to email | 1. Open website 2. Click contact button 3. Click on the email button | Major | Minor | https://drive.google.com/file/d/15BLK7u-SpAMEyAw3QvI4os9xinWz7D_4/view?usp=drive_link | New
DEF_MSM_HP_14 | MSM_CU_14 | keep in touch name should not accept any numbers or special characters | Accepts numbers and special characters | 1. Open website 2. Click contact button 3.Type on numeric and special characters | Major | Major | https://drive.google.com/file/d/1YFj0E9ST28CAsnwW5n9iIQdp-KC6A06G/view?usp=drive_link | New
DEF_MSM_HP_15 | MSM_CU_15 | keep in touch phone field should not accept alphabets | Accepts alphabets | 1. Open website 2. Click contact button 3.Type alphabets | Major | Major | https://drive.google.com/file/d/1AACyL1tm65bvFKoIb4K1ZtVIWxZx9UFD/view?usp=drive_link | New
DEF_MSM_HP_16 | MSM_CU_16 | keep in touch phone field should not accept morethan 13 numbers | Accepts morethan 13 numbers | 1. Open website 2. Click contact button 3.Type 13 numbers | Major | Major | https://drive.google.com/file/d/1YFj0E9ST28CAsnwW5n9iIQdp-KC6A06G/view?usp=drive_link | New

## DEFECT_DISTRIBUTION
MAYURA SUPER MARKET
Module Name | Defect_Distribution
Home | 6
About_us | 5
Brands | 0
Offers | 0
Contact_us | 5

## TEST_REPORT
MAYURA SUPER MARKET
Module Name | Passed TC | Failed TC | Total TC
Home | 14 | 6 | 20
About_us | 15 | 5 | 20
Brands | 11 | 0 | 11
Offers | 7 | 0 | 7
Contact_us | 13 | 5 | 18